## Sheet1
Functional Requirements
| Spec no. | D or W | Date added/modified | Description | Spec | Responsibility | Test/Verification | Result:
| 1 | W | 2019-01-19 | Can estimate the number of fishes fishes in the area. | Able to sense the presence of one or multiple fishes within a specified vicinity | Wei Chun, Cheng Chei | Through temperture sensor relaying data back to boat. | Met
| 2 | D | 2019-01-19 | Dispense fish food when button is pressed | Dispenses I kg of fish food 1 time when button is pressed | Cheng Chei | Bottle rotates and dispenses the fish food ( the system should be modify to be able to dispense more food mutiple times) | Met
| 3 | D | 2019-01-19 | Attach fishing line to craft and release line when fishes are detected. | A clip that dispenses the fishing line when button is pressed | Linjie | Servo rotates to allow fishing line to be released | Met
| 4 | W | 2019-01-19 | Design for ease of maintance, debugging and troubleshooting. | The wiring should be simple and clear with labers and the recharging of batt | Linjie, Caleb | User finds the design convenient for troubleshooting hardware | Met
| 5 | D | 2019-01-19 | Floats on water and is stable when stationary or moving. | Floats stabaly on water surface when stationary and moving, the main body should be 10mm above water level with addition load of 2kg. | Linjie | Does not waver or shake when moving or stationary with a low centre of gravity, the main body is above the water level. | Met
| 6 | D | 2019-01-19 | Can move by remote control wirelessly | Using IR sensor and remote to control craft's movement and direction ( control disstance longer than 100m) | Cheng Chei | Pressing buttons will make the motors rotate in the intended directions. However, the control distance is just around 5m. Should use ESP-32) | Not Met
Constraints
| Spec no. | D or W | Date added/modified | Description | Spec | Responsibility | Test/Verification | Result
| 1 | W | 2019-01-19 | Does not exceed budget of $100 | Spend withing 100SGD | Caleb | Calculate total expenses from reciepts | Met
| 2 | D | 2019-01-19 | Has no exposed wires/electronics | Wires and electronics must be protected from water through waterproof materials | Wei Chun | Looking for any exposed wires or electronics | Met
| 3 | D | 2019-01-19 | Does not exceed total size of 1000x1000x1000 | Craft must be within 1000x1000x1000 | Lin Jie | Use a meter long ruler | Met
| 4 | D | 2019-01-19 | No sharp edges | Craft does not have any sharp potrusions | Caleb | File down or fillet any sharp edges | Met
| 5 | D | 2019-01-19 | Sufficient water-proofing of electronics | No exposed wires and water can leak into main electronic body | Jason, Wei Chun | Using appropriate tubing, wiring and epoxy to ensure it is waterproof | Met